## Task
Sl. No. | Company | Module | Menu | Task | Weight | Status | Assigned To | Hours | Type | Done Date | Note | Requirement Given By | Collected By | Approved By | Collected On | Documented By | Documented On | Dev.Req.Date | Deadline | QA | Assigned QA | Client Delivery Date
1 | Kolpolok | hr_empoyee | employee creation | System for import data from excel file to create employee | 9 | Done | Imtiaj | 8 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
2 | Kolpolok | hr_empoyee | employee creation | Add new fields in the excel file | 9 | Done | Imtiaj | 8 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
3 | Kolpolok | hr_empoyee | employee creation | add mandatory colums in employee creation (14 columns) | 6 | Done | Imtiaj | 4 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | Working | Prema Apu | 2023-09-18
4 | Kolpolok | hr_empoyee | employee creation | work location list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | Working | Prema Apu | 2023-09-18
5 | Kolpolok | hr_empoyee | employee creation | designation list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
6 | Kolpolok | hr_empoyee | employee creation | department list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
7 | Kolpolok | hr_empoyee | employee creation | team list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
8 | Kolpolok | hr_empoyee | employee creation | employee type will be Probation, Permanent, Contructual, Internship | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
9 | Kolpolok | hr_empoyee | employee creation | Employee duration in the company will be changed into job tanure and will calculate the ducation automatically | 3 | Done | Imtiaj | 1 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
10 | Kolpolok | hr_empoyee | employee creation | Official phone number will be changed into work phone | 1 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
11 | Kolpolok | hr_empoyee | employee creation | Official email number will be changed into work email | 1 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
12 | Kolpolok | hr_empoyee | employee creation | supervisor name list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
13 | Kolpolok | hr_empoyee | employee creation | worklocation will be removed | 1 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
14 | Kolpolok | hr_empoyee | employee creation | In address present address and permanent address will be added | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
15 | Kolpolok | hr_empoyee | employee creation | personal phone number and personal email field will be added | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
16 | Kolpolok | hr_empoyee | employee creation | language, work distance, education, work parmit, other fields in marital status will be removed | 4 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
17 | Kolpolok | hr_empoyee | employee creation | new fields will be added in emergency contract from employee excel sheet | 3 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
18 | Kolpolok | hr_empoyee | employee creation | citizenship will be changed into other information | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
19 | Kolpolok | hr_empoyee | employee creation | place of brith and country of birth will be removed | 1 | Hold | Imtiaj | 0 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
20 | Kolpolok | hr_empoyee | employee creation | Age will be added and auto calculated | 3 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
21 | Kolpolok | hr_empoyee | employee creation | in employee list view in left side filter depertmnet wise will be changed into team wise | 4 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-12 | 2023-09-18 | 2023-09-18 | To-do | Prema Apu | 2023-09-18
22 | Kolpolok
23 | Kolpolok | [6 empty] | 35 | 4.375
24 | Kolpolok
25 | Kolpolok | hr_empoyee in odoo 13 | employee creation | System for import data from excel file to create employee | 9 | Done | Imtiaj | 8 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
26 | Kolpolok | hr_empoyee in odoo 14 | employee creation | Add new fields in the excel file | 9 | Done | Imtiaj | 8 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
27 | Kolpolok | hr_empoyee in odoo 15 | employee creation | add mandatory colums in employee creation (14 columns) | 6 | Done | Imtiaj | 4 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | Working | Prema Apu | 2023-09-24
28 | Kolpolok | hr_empoyee in odoo 16 | employee creation | work location list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | Working | Prema Apu | 2023-09-24
29 | Kolpolok | hr_empoyee in odoo 17 | employee creation | designation list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
30 | Kolpolok | hr_empoyee in odoo 18 | employee creation | department list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
31 | Kolpolok | hr_empoyee in odoo 19 | employee creation | team list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
32 | Kolpolok | hr_empoyee in odoo 20 | employee creation | employee type will be Probation, Permanent, Contructual, Internship | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
33 | Kolpolok | hr_empoyee in odoo 21 | employee creation | Employee duration in the company will be changed into job tanure and will calculate the duration automatically | 3 | Done | Imtiaj | 1 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
34 | Kolpolok | hr_empoyee in odoo 22 | employee creation | Official phone number will be changed into work phone | 1 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
35 | Kolpolok | hr_empoyee in odoo 23 | employee creation | Official email number will be changed into work email | 1 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
36 | Kolpolok | hr_empoyee in odoo 24 | employee creation | supervisor name list | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
37 | Kolpolok | hr_empoyee in odoo 25 | employee creation | worklocation will be removed | 1 | Hold | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
38 | Kolpolok | hr_empoyee in odoo 26 | employee creation | In address present address and permanent address will be added | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
39 | Kolpolok | hr_empoyee in odoo 27 | employee creation | personal phone number and personal email field will be added | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
40 | Kolpolok | hr_empoyee in odoo 28 | employee creation | language, work distance, education, work parmit, other fields in marital status will be removed | 4 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
41 | Kolpolok | hr_empoyee in odoo 29 | employee creation | new fields will be added in emergency contract from employee excel sheet | 3 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
42 | Kolpolok | hr_empoyee in odoo 30 | employee creation | citizenship will be changed into other information | 2 | Done | Imtiaj | 0.5 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
43 | Kolpolok | hr_empoyee in odoo 31 | employee creation | place of brith and country of birth will be removed | 1 | Hold | Imtiaj | 0 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
44 | Kolpolok | hr_empoyee in odoo 32 | employee creation | Age will be added and auto calculated | 3 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
45 | Kolpolok | hr_empoyee in odoo 33 | employee creation | in employee list view in left side filter depertmnet wise will be changed into team wise | 4 | Done | Imtiaj | 2 | New Requirement |  |  | Anik Bhi | Imtiaj | Bari Bhi | 2023-09-11 | Imtiaj | 2023-09-20 | 2023-09-24 | 2023-09-24 | To-do | Prema Apu | 2023-09-24
46 | Kolpolok
47 | Kolpolok
48 | Kolpolok
49 | Kolpolok
50 | Kolpolok
51 | Kolpolok
52 | Kolpolok
53 | Kolpolok
54 | Kolpolok
55 | Kolpolok
56 | Kolpolok
57 | Kolpolok

## Feedback on Mandatory Columns
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester
HR001 | Number Saving issue | In Private Contact part, employee's personal number isn't being saved | 1
HR002 | Employee type issue | In HR setting portion, selecting the expected employee type, gives a error output | 2
HR003 | Invalid number issue | In Office phone field, after giving invalid input, phone field is being saved | 3
HR004 | Invalid mail issue | In Office email field, after entering invalid mail input , its taking wrong input and saved | 4

## Feedback on Employee Creation
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester
HR001 | Field missing issue | In Bank info of Employee create , add a another field for nominee email addess. | 1
HR002 | Saving issue | In employee create Official record part of the HR requirements, After fill the all mandatory field employee create not saving | 2 | fixed | Fixed
HR003 | LImited input issue | In employee create part, resume part , taking limited number input | 3 | fixed | fixed
HR004 | Placement issue | In employee create part ,resume part, Type and display type field should be placed at first before institute | 4
HR005 | Empty field issue | In skill part of employee create part, there is no field exist for progress | 5
HR006 | Wrong selection bar | In Personal information of employee create part ,the selection bar suggestion is not private address related | 6
HR007 | Box size issue | In personal information of employee create part, Housing status field size isn't same than other field | 7
HR008

## Feedback on User_Profile
No. | Issue Name | Issue Details | image/video link | Priority | Developer Status | Tester
HR001 | Reset password | In Odoo Login page, when user wants to reset password, it doesn't work | 1 | High
HR002 | Remove Create option | In Odoo employee creation, when the reporting manager list are showing, create option is also showing | 2 | Low
HR003 | Same name saving | In Odoo employee creation, when entering a name in employee's name,two same names are saving together | 3 | Medium
HR004 | Name field change issue | In Odoo employee creation, in private information part home address filed name needs to be changed | 4 | High | fixed | Fixed
HR005 | Email Validation | In Odoo employee creation, in private information part,when employee update email address,email field should be validated | 5 | High
HR006 | Invalid Phone | In Odoo employee creation, in private information part , inputing invalid ten digit phone number is being saved | 6 | High
HR007 | Invalid Phone | In Odoo employee creation, in private information part , inputing invalid alphabetic character phone number is being saved | 7 | High
HR008 | Remove Create Option | In Odoo employee creation,private information ,in employee's bank account number create option should be removed | 8 | High | fixed
HR009 | Remove Create Option | In Odoo employee profile creation, resume part, Skill create option should be removed | 9 | Medium
HR010 | Remove Create Option | In Odoo employee profile creation, resume part, in Skill level create option should be removed | 10 | Medium
HR011 | Save bug issue | In Odoo employee profile creation, update private information isn't being saved |  | High | fixed | fixed
HR012 | Wrong calculation | In Odoo user time off request, time off day duration took wrong calculation |  | High
HR013 | Limited input | In Odoo user profile, Section field taking limited input | 13 | High
HR014 | Limited input | In Odoo user profile, Grade field taking limited input |  | High
HR015
HR016
HR017
HR018

## Changes_Requirements
Requirement no | Requirement name | Development Status | Tester | Bug SS
REQ001 | Profile photo should be bigger | Fixed | Fixed
REQ002 | The logo of Kolpolok should be placed in the logo of the login page | Fixed | Fixed
REQ003 | In employee profile, employee can set their skills and Supervisor will set the skill priority | No need to be changed
REQ004 | In employee profile , this section will be added under Work Team,they are (1)Department, (2)Section, (3)Grade | Fixed | Fixed
REQ005 | In employee profile, Some term will be changed .(1) Official phone will be placed in office phone, (2)Official Email will be placed in office email | Fixed | Fixed
REQ006 | In employee private information, Religion, Personal email, Personal phone will be added | Fixed | Fixed
REQ007 | Spelling mistake issue- employee private information: Emergency Contact | Fixed | Fixed
REQ008 | In employee private information, Generic address should be changed in Home address | Fixed | Fixed
REQ009 | The time off record list will be generated Descending order | Fixed | Not fixed | 9
REQ010 | Leave manager landing page should be dashboard | Fixed | Fixed
REQ011 | While making changes from employee profile it shows not allowed | Fixed
REQ012 | In time off while in approval state leave deduction issue | Fixed | Not fixed | 12
REQ013 | Organization Chart View | No need to be changed
REQ014 | In employee profile , this section will be added under Work Information- Location,they are (1)Date of joining, (2)Probation period, (3)Confirmation Due Date, (4)Job Tenure, (5)Employment type | Fixed | Fixed
REQ015 | Approved/ Refused leave need to be shown different color(Approve- Green, Pending-Black, Refused-Red with leave type ,total leave number My Time Off
REQ016 | Need to be arrange leave by upcoming new one
REQ017 | A notification need to be sent to employee when leave & other application will approved/refused
REQ018 | Employee Team--> Team name | fixed | fixed
REQ019 | Duration count wrong for User | fixed
REQ020 | Official record group with new fields | fixed | fixed
REQ021 | Responsibles--> Reporting Manager--Name, Designation | fixed | fixed
REQ022 | Employee Department--> Department | fixed | fixed
REQ023 | Emergency Contact | fixed | fixed
REQ024 | Bank acoount will be blocked | fixed | fixed
REQ025 | NID will be all capital letter | fixed | fixed
REQ026 | Institution will be changed | fixed | fixed
REQ027 | In employee users login there will be no everyone timeoff | fixed | fixed
REQ028 | Time off type name will be changed | fixed | fixed
REQ029 | New allocation request button hide | fixed | fixed
REQ030 | Email Notification of leave approval notice
REQ031 | Directory will be like user profile
REQ032 | Edit option will be off in the future
REQ033 | Leave Manager Subordinate time off
REQ034 | State will be showen in calender | fixed

## Time_Off_Bug
No. | Issue Name | Issue Details | image/video link | Priority | Developer Status | Tester
HR001 |  | In time off portion, time off calender showing fewer holidays after taking the total time off days are approved | 1